## Sheet1
Goals, Actions | Current Status DONE= complete, ONGOING = something that has started and met commitments, but happens on a regular schedule or requires continuous work, DEVELOPING = starting work, not yet complete | Updates | Responsible person if not yet completed
Diversity, Equity and Inclusion Strategic Plan Updates
Increase recruitment of students, staff and faculty from historically marginalized groups
1) Continue to develop focused student outreach and related partnerships and financial aid initiatives | Ongoing | Joined American Talent Initiative to increase graduation/thriving of low-income students; establishment of the PLAID Program for First-Generation/Limited-Income Students liaisoning DoS and CDI | Scott Friedhoff
2) Review online and other materials to ensure high-quality information for prospective students, faculty and staff regarding diversity, equity and inclusion | Ongoing | New page on Diversity, Equity and Inclusion created. Additional materials in process with a view to sharing updates with students/faculty/staff more efficiently/frequently. | Melissa Anderson
3) All hiring departments, managers and chairs will participate in training to develop skills in recruiting diverse applicant pools, mitigating implicit bias, and mentoring inclusively and effectively. (Faculty: 2017-18, Staff: ongoing, starting 2018 with support from Human Resources in searches) | Ongoing | All hiring academic departments and 15 others completed 4 half-day workshops. CDEIO initiated first staff inclusion training for new hires in June 2019. CDEIO inclusion training in progress for staff divisions. | Lisa Perfetti, Human Resources, Ivonne García
4) Raise funds to create target of opportunity faculty hires | Ongoing | Perry-Williams fellowship funds 2017; Mellon grant for four positions received June 2018; other funds still being sought | Sarah Bolton
5) Join consortia such as Compact for Faculty Diversity and National Center for Faculty Development & Diversity | Done
Broaden and deepen educational programs to improve cultural competencies and to increase professional effectiveness in diversity, equity and inclusion.
1) Periodic educational programs on various facets of diversity, equity and inclusion for staff and faculty, as appropriate for roles/responsibilities | Ongoing | Inclusive classrooms program for all faculty in faculty meetings. Several individual academic departments also engaged. Wooster is collaborating with the other OH 5 colleges in a Mellon-funded program that includes a workshop on May 23 and a follow-up session on August 6 to develop a plan for training for diversity coaches who will provide mentoring to faculty and staff on working with “New Majority” students. Training for all staff in HR, Student Affairs, President's cabinet, APEX & library with external trainer in spring 2018. 50 additional staff have also undertaken training with this facilitator. Additional training being brought by CDEIO to departments, to tenure committee, to department chairs, and to search chairs. | Ivonne García/Lisa Perfetti
2) Training for department chairs and managers on supporting diverse faculty and staff and creating/maintaining an equitable and inclusive working environment | Ongoing | Training for all hiring dept's in place on recruitment, training on creating equitable and inclusive working environments ongoing | Ivonne García/Lisa Perfetti
3) Regular workshops for faculty on inclusive pedagogy, within departments and across the College | Ongoing | inclusive pedagogy workshops in teaching matters & faculty meeting. All departments expected to undertake learning in inclusive pedagogy in their fields. | Ivonne García/Christa Craven
4) Effective programs on diversity, inclusivity and community, for all first-year students and for RAs and other student leaders | Ongoing | New, revised and expanded programs rolled out for orientation in 2019, and 2020. CDEIO trained all RAs, OCers, Tour Guides, ARCHERS and will be doing further training of student mentors. | Nathan Fein/Julia Zimmer/Ivonne García
5) Strengthen collaborations with the City of the Wooster regarding diversity and inclusion, particularly through sharing educational programs we bring here with local schools | Ongoing | President and CDEIO working with the mayor and city officials. | Sarah Bolton/Ivonne García
6) Coordinate and advertise diversity and equity-related programming across campus to all constituencies (begun, will work through student and staff/faculty advisory groups) | Ongoing | This programming is tagged in the new campus calendar and is being advertised much more broadly | Melissa Anderson
Strengthen Resources for work on diversity, equity and inclusion and for support of community members from underrepresented groups
1) Provide dedicated staff to support diversity, equity and inclusion work. | Ongoing | CDI directors and CDEIO have hired student interns to support the campus-wide work on diversity. | Sarah Bolton
A. Hire one additional person with broad oversight of programs and assessments, reporting to President, with expertise relevant to staff and faculty as well as student experiences. | Done | CDEIO hired
B. Restructure to create dedicated staff for students within CDI | Done | Additional staff (assistant director, program coordinator) hired to support International Student Services in 2019.
2) Create an ongoing committee of students, staff and faculty to advise on diversity, equity and inclusion and to coordinate some programming opportunities | Done - student advisory group needs to be updated | Two committees developed, DEI advisory committee for staff/faculty, and parallel committee for students. Staff/faculty committee discusses staff/faculty training and support, and led CDEIO search. Inclusion action team formed. Student advisory body needs to be formed. Best structure is being discussed with MSOC | Amanda Panaiagua/Ivonne García
3) Build programs and train student affairs staff broadly to effectively support 1st generation, low income, LGBTQ+, and international students and students of color | Ongoing | Two days of training with external trainer - Feb and April 2018, annual; CDEIO did inclusive team-building workshop for DOS in spring 2019 | Ivonne García, Myrna Hernandez
4) Broaden and deepen programs for faculty and staff from historically marginalized groups, including on campus and through Ohio 5 and GLCA consortia | Ongoing | Ohio 5 gatherings for faculty of color established and continuing. Regular programs each semester at Wooster enacted by CDEIO and Dean for Faculty Development | Ivonne García, Christa Craven, Lisa Perfetti
Define responsibilities across campus: include diversity, equity and inclusion work as part of the regular assessments and plans for individuals and departments
1) Human Resources staff will develop ways to include diversity, equity and inclusion work as part of all regular staff annual evaluations as appropriate to roles | Developing | In place for cabinet members and student affairs staff. Tools being developed for all staff. | Lorraine Forcinito/Jim Prince
2) The Teaching Staff and Tenure Committee will consider ways of including diversity, equity and inclusion efforts in faculty reviews and biannual reporting | Ongoing - initial changes complete | The language in the template for the biannual reviews was changed to encourage faculty to report on invisible service and to require every faculty member to address how they contributed to diversity, equity and inclusion efforts during the two-year period. In addition, TS&T changed the language in the letters that are sent to faculty who are up for review and to their chairs to encourage providing information about invisible service and contributions to diversity in the review process. Diversity advocates added for all tenure and promotion reviews. | Lisa Perfetti, Ivonne García
3) The Educational Policy Committee will develop ways for academic departments and programs to include diversity, equity and inclusion in goals within their annual plans and assessments, and in external reviews. | Done | Done for academic department reviews.
Create Policies and programs for equitable access
1) Develop policy on gender-neutral facilities, and monitor progress toward any needed facilities | Done
2) External review of disability support services and ADA compliance | Developing | To take place Fall 2020 | Sarah Bolton, Ivonne García
3) Create timetable/plan for improving accessibility of facilities | Underway - in process | Included in Campus Master planning (happening fall 2019) | Master plan will be completed in fall 2020, Jim Prince, Sarah Bolton
4) Review/update/communicate bias incident and discrimination reporting and response processes | Underway - in process | Bias Incident Response Team created 1/2018. Draft of new policy and process for all discrimination-based harassment/harm for faculty, staff and students complete. Will review with students/staff/faculty fall 2020 and implement immediately | Ivonne García
Communicate
1) Communicate mission statement, resources and progress on a website that would be helpful to those considering coming to Wooster as well as to those already here | Ongoing | New website that more fully describes mission, purpose and goals of DEI at Wooster , updates ongoing | Melissa Anderson, Ivonne García
2) Report annually to the community | Ongoing | Each year, starting with spring 2018 | Ivonne García
Additional items added since the DEISP plan's development
Galpin Call -In and other spring 2018 discusions
Add lights, signage, cameras and additional coverage for Beall avenue safety | Ongoing | New sets of Lights, cameras and signage added. Additional SPS coverage in process | Additional SPS coverage: funding responsibility S. Bolton, Hiring responsibility S. Glick
Additional resources for student groups who provide support for DEI | Done | Additional funding for CDI provided, review of funding by CC/SGA undertaken, housing process improved for group housing, new group houses for several student groups who support work related to DEI
Cultural competency training for student org leaders | Ongoing | Annual - 2019 training will be done by CDEIO | Amanda Panaiagua, Ivonne García
Sanctioning guidelines for bias-related harassment | Done | Completed and added to Scot's Key, 2019
Campus climate survey | Done | Completed fall 2019. Will repeat in 2021 | Ivonne García
Monthly climate report | Done
Website translation | Done
International student needs; storage, insurance, ELL support | Done | New, more robust storage option developed and implemented; more robust health insurance option for international and DACA students obtained; 2nd ELL staff member approved and recruited
Curricular change to strengthen learning of all students about diversity, power and privilege | Done | Diversity, power and priviledge requirement voted in spring 2018, implemented
Latinx Town Hall - September 17, 2019
Latinx space | Done | Space indentified and committed, funds committed, facilities working on getting space converted for this use.
Latinx counselor in the wellness center | Developing | Exploring possibilities for meeting this need | Bolton, García
Point person for Latinx student concerns | Done
Event funding | Done
More Latinx curriculum, major in Latin American Studies | Developing | Discussion with faculty November 2019. | Ivonne García/Lisa Perfetti
More Latinx faculty | Ongoing | Programs to increase faculty diversity in process, continue to result in increasing numbers of Latinx faculty. Faculty retention study completed, Provost has developed plans to address concerns identified, is discussing with the faculty members; faculty cohort mentoring program established summer 2019 in response to the study | Lisa Perfetti, Ivonne García, Christa Craven
Student retention | Ongoing | Inclusion action team and retention work group focussing charged with strengthening retention for all students | Myrna Hernandez, Ivonne García
Needs of First Generation/Low income students | Ongoing | PLAID program established, additional work on improving equity of access to programs and opportunities continuing | Shadra Smith
DEI Town Hall - October 23rd, 2019
Faster response times, for SPS publicize priorities and expectations around time to increase responsiveness | Ongoing | SPS reaffirmed that they will not say "no" to those who call, and will communicate clearly how quickly they can be there. It should never be more than 10-15 minutes unless there is a major emergency on campus. Those who call with safety concerns are prioritized. Additional ways to improve response times being established. | Steve Glick
Prioritize SPS outside library at 2 am as people leaving then need safe way home | Done
Allow students to park in faculty/staff lots after hours for safety | Done
More comprehensive language and training around processes in Scot's key; make processes transparent | Ongoing | Scot's key revised so that students bringing concerns get information about outcomes and reasons, and have the right to appeal (2019). New Bias and discrimination process written, will be reviewed with students for clarity and for concerns before finalizing. To be completed in Fall 2020
Attendance policies; policies around events on DEI as extra credit or required for courses | Developing | Being discussed with faculty at faculty meeting, Nov. 4th | Ivonne García/ Jen Bowen
Increase availability and diversity of counselors | Ongoing | 4th counselor added spring 2019. No wait list since that time. Seeking ways to have additional support with counselors of diverse identities | Myrna Hernandez/Ivonne García
Transparency regarding wellness costs and availability | Done | Exploring how best to do this, as there are differences depending on insurance and details of procedures.
Safety trainings for those who are being targeted | Developing | Seeking options for high -quality training of this kind | Sarah Bolton
Relationship with the City - collaboration with City officials to improve climate and responsiveness | Ongoing |  | Sarah Bolton/Ivonne García
Make MSOC formal in advisory role to Dr. García | Ongoing | Discussed with MSOC 10/29 - they are not sure they want the role structured in this way. Dr. García to continue to work with students to determine what is best. | Amanda Panaiagua
Diversity in SPS hiring | Ongoing | Diversity in hiring continues to be top priority, working through NAACP and other local and regional organizations to build pools. New dispatcher who brings more diversity to the department hired 10/31/19 | Joe Kirk
More artwork around campus with representation of marginalized groups | Developing | Develop an approach to art for spaces with student advisory group | Sarah Bolton/Mike Taylor by December 1, 2020
Security and Protective Services Discussion - October 27th, 2019
Additional cameras | Done | 40+ cameras added | Steve Glick
Demographic Information about who is stopped collected and reported | Done | Information being collected as of 10/28/2019. Will be reported at the end of each semester and reviewed by CDEIO for indications of bias/profiling/discrimination.
Names and shifts of all officers publicized | Done | On SPS website as of Monday, 10/28/2019
SPS officers trained to prevent bias/discrimination | Ongoing | Will do regularly each semester. Done spring 2018, November 2019, spring 2020 | Steve Glick/Myrna Hernandez
Summer 2020 Disucssions
SPS structure and relationship to police. Minimize police presence on campus | Developing | External review of SPS policies completed with Dr. Hardaway. Structural changes to be complete by 8/15/2020 | Sarah Bolton, Myrna Hernandez
Hire more Black staff and faculty | Ongoing | Required anti-bias training, diversity advocates, proactively inclusive hiring processes in place for faculty; will enact for staff searches this year. | Sarah Bolton
Ombudsman / accountability for managers and leaders | Developing | Outside ombudsperson possibility interviewed; will put in place for fall 2020 | Sarah Bolton, Ivonne García
Contributions to diversity, equity and inclusion will be part of professional assessments for all faculty and staff. Building and supporting a diverse team, proactively creating an inclusive culture, ongoing learning and action will be part of the evaluations of all campus managers and leaders. | Developing | Will be completed for evaluation cycle of 2020-2021 academic year | Sarah Bolton, Lisa Perfetti, Lorraine Forcinito
Immediately implement new fundraising for Africana studies, scholarships, Black Student Equity Fund, funds for DACA and international students | Done |  | Sarah Bolton, Wayne Webster
Increase availability of counselors of color | Developing | Have reached out to local counselors of color to set up additional counseling hours at Longbrake | Ivonne García, Ray Tucker
Revise new student orientation and leadership training for RAs and student organizations to strengthen learning about racism, cultural competency and creating inclusive community | Done